# THE INAUGURAL

# COMMUNITY PHARMACY STAKEHOLDER FORUM

15 November 2016

Pharmacy Diabetes Screening Trial

# Project team

## EXPERT PANEL

The Expert Panel provides advice and direction on the implementation of the trial. The project team will work closely with the Expert Panel throughout the trial.

The functions of the Expert Panel include providing guidance on:

- practicalities of the proposed trial design

- communication strategies over the life of the trial

- how best to engage with trial participants

- how to support engagement, recruitment, retention of participants, general practitioners, community pharmacies and other relevant health professionals

### Expert panel: chair and representatives

Chair

Professor Stephen Colagiuri,

Professor of Metabolic Health and Co-Director of The Boden Institute at University of Sydney.

Members

Associate Professor Sof Andrikopoulos, Australian Diabetes Society. Kirrily Chambers, Australian Diabetes Educators Association.

Dr Gary Deed, Royal Australian College of General Practitioners. Teresa Di Franco, Pharmaceutical Society of Australia.

Amanda Galbraith, Community Pharmacist.

Adjunct Professor Greg Johnson, Diabetes Australia. Professor Ines Krass, Representative of the Project Partners.

Observers

Katrina Howe, Department of Health (observer). Julianne Quaine, Department of Health (observer).

Emeritus Professor Lloyd Sansom AO, Trials Advisory Group (observer).

# Objective

To assess the comparative clinical effectiveness and

cost-effectiveness of three different pharmacy-delivered models of opportunistic assessment for diabetes in an asymptomatic, previously undiagnosed population.

# Hypothesis

The addition of either a HbA1c Point of Care (POC) test or scBGT POC test to the AUSDRISK assessment is associated with a statistically significant increase in the proportion of new cases of diagnosed type 2 diabetes mellitus (T2DM) and will be more cost effective than the AUSDRISK assessment alone.

# Outcomes

- Primary

  - The difference in proportions of newly diagnosed T2DM cases between the two intervention arms and the comparator arm (to be identified by the subsequent GP assessment and blood test results)

  - Secondary

  - Proportion of newly diagnosed cases of impaired fasting glucose (IFG) or impaired glucose tolerance (IGT)

  - Proportion of people referred to the GP

  - Proportion who take up the referral to the GP

## Overview: Trial design is a Clustered RCT

# Trial Groups

GROUP A:

- AUSDRISK assessment tool alone

- Referral to a GP if AUSDRISK ≥ 12

GROUP B:

- AUSDRISK assessment tool +

- HbA1c point-of-care (POC) test in patients with AUSDRISK ≥ 12

- Referral to a GP if HbA1c ≥ 5.7% (39 mmol/mol) is detected**

GROUP C:

- AUSDRISK assessment tool +

- small capillary blood glucose test (scBGT) in patients with AUSDRISK ≥ 12

- Referral to a GP if

  - fasting blood glucose (FBG) ≥ 5.5mmol/l** or

  - random blood glucose (RBG) ≥ 7.8 mmol/l**

# Trial design

## Geographical areas are the unit of randomisation

- Randomised to Group A, B or C

- Stratified by metro/regional/remote residential areas

- Pharmacies in the selected areas will be invited to participate

## Patients are the unit of analysis and recruited as follows:

- According to the distribution of the Australian population

•	By age groups (35-44, 45-54, 55-64, & 65-74)

- By gender

# Pharmacy inclusion/exclusion criteria

- Approved Section 90 pharmacy

- Appropriate private area in the pharmacy

- Appropriate storage and disposal of reagents and consumables

- Accredited by an approved Pharmacy Accreditation Program

- Agree to adhere to standards, terms and conditions, guidelines and protocols

- Endeavour to include the Pharmacy Diabetes Screening Trial CPD training in annual training plans as appropriate

- Agree to obtain written patient consent and to provide data required for evaluation of the trial

# Pharmacy Recruitment Targets

| State/Territory | Major Cities Regional Remote Total | Regional | Remote |  | Total |  |
| --- | --- | --- | --- | --- | --- | --- |
| New South Wales | 80 | 25 |  | 3 |  | 108 |
| Victoria | 59 | 24 |  | 2 |  | 85 |
| Queensland | 38 | 31 |  | 5 |  | 74 |
| South Australia | 14 | 9 |  | 7 |  | 30 |
| Western Australia | 22 | 6 |  | 6 |  | 34 |
| Tasmania | 0 | 10 |  | 3 |  | 13 |
| Northern Territory | 0 | 7 |  | 4 |  | 11 |
| Australian Capital Territory | 8 | 0 |  | 0 |  | 8 |
| Total | 221 | 112 |  | 30 |  | 363 |

# Inclusion/Exclusion Criteria – Screening Participants

## Trial Sample – Screening Participants

# Evaluation – Baseline, Formative and Process

| Type of evaluation | Description/measure | Data source |
| --- | --- | --- |
| Baseline data | Survey of current screening services provision of participating pharmacies | Web based self-completion questionnaire |
| Formative | To identify (a) overall experience, with service implementation, any difficulties with compliance, and options for overcoming these; and (b) perceptions of sustainability of the screening model, and requirements for sustainability | Qualitative interviews with a 10% sample of participating pharmacists/pharmacy staff |
| Process | Median number of trial screening services/pharmacy/week | Pharmacy records |
|  | Total number of trial screening services per pharmacy | Pharmacy records |
|  | % with elevated risk who received appropriate further screening and who were referred to the GP for further assessment | Pharmacy records |
|  | % who were screened who were referred to evidence based lifestyle modification programs in pharmacy or elsewhere | Pharmacy records |
|  | Patient satisfaction with the pharmacy screening service | Follow up survey of a 10% sample of all screening participants |

# Evaluation – Clinical Outcomes and Economic Analysis

# Incentive Payments

| Group | No. participants | Component of service | $ | Total $ per service |
| --- | --- | --- | --- | --- |
| Group A | 10240 | Initial screen only | 10.00 | 10.00 |
|  |  | Referral | 11.00 | 21.00 |
| Group B | 10240 | Initial screen only | 10.00 | 10.00 |
|  |  | POC testing | 10.50 | 20.50 |
|  |  | Referral | 11.00 | 31.50 |
| Group C | 10240 | Initial screen only | 10.00 | 10.00 |
|  |  | POC testing | 10.50 | 20.50 |
|  |  | Referral | 11.00 | 31.50 |

A bonus of $750.00 will also be provided to the pharmacies as an incentive to maintain the quality of the collected data e.g., payable upon the completeness of the data collected according to the protocol

# Human Ethics Approval

- Application has been approved

  - Participant Information Statement (PIS) for pharmacies/pharmacists

  - Pharmacy/pharmacist consent form

  - PIS for screening participants

  - Screening participant consent form

  - GP information/engagement letter

  - GP Referral

  - Pharmacy baseline survey

  - Patient 3 month follow up survey

# Dept of Human Resources Approval

## Application to use participant Medicare Data has been approved:

- Medicare Consent Form

## Medicare Data will be used to:

- Verify clinical outcomes

- Conduct economic analyses

# Training Requirements

# Resources for Participating Pharmacies

Promotional and Printed Material

- Posters

- Flyers

- PIS

- Consent Forms

- GP Letters

- Eligibility Cards

- Brochure Stands

Equipment and Devices

- Point of Care Devices, Waist Measurement Tape, and Consumables

- Tender process based on an open request for proposals.

- Currently being reviewed by Pharmacy Guild, Research Team and Expert Panel

Promotional Material In Pharmacy

Promotional Material In Pharmacy

Promotional Material In Pharmacy

# Summary of progress

Human Ethics final approval received – University of Sydney

Medicare data final approval received – Department of Human Resources

Online training – Available on Guild Academy

Checklists for device competency – Research Team

Accredited CPD points – Pharmaceutical Society of Australia

Online baseline survey developed – Research Team

Standard Operating Procedures (SOPs) and Flowcharts – Research Team

Pharmacy Operations Manual and Workbook – Research Team

Printed resources for pharmacies (PIS, consent forms, flyers, posters, GP letters, etc) - Guild

Random sample of pharmacies generated – Research Team

Invitation and recruitment of pharmacies from random sample – Guild

GuildCare Pharmacy Diabetes Screening Trial software - Guild

Tender for point of care devices and other resources/consumables for pharmacies - Guild